## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project
|  | 2 | LLM for Contract analysis
|  | 3 | Clause Identification and Risk Analysis Engine
|  | 4 | Update tracking and Contract Modification
Note on F1: ====== ID#AAABv6zxcdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28
]
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 46381 | 0 | 0 | 0 | 46386 | 46387 | 46023 | 46024 | 46025 | 46026 | 46027 | 46028 | 46029 | 46030
SPRINT 1 BACKLOG
[9 empty] | Nov 10th | Nov 11th | Nov 12th | Nov 13th | Nov 14th | Nov 15th | Nov 16th | Nov 17th | Nov 18th | Nov 19th | Nov 20th | Nov 21th | Nov 22nd | Nov 23rd
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Tanisha Bhardwaj | practiced all fundamentals required for project | Done |  | Introduction Session | Python and Jupyter Installation done | Brief Knowledge about keywords and naming conventions | Understanding about variables and how to work on agile sheet | Understanding of storing values in variables in different ways, knowledge about data types and different data structures. | revision of data structures and its use cases | Revision of all previous topics | Brief discussion about range data type and function and its use cases with immutable and mutable type and flow control and conditonal statements usecases | Understanding about loops and functions | brief discussion on functions and its types | Brief discussion on import, from and as kewords | Brief discussion on oops concepts | Different types of constructors | Revision on previous topics
[9 empty] | Nov 25th | Nov 26th | Nov 27th | Nov 28th | Nov 29th | Nov 30th | Dec 1st | Dec 2nd | Dec 3rd | Dec 4th | Dec 5th | Dec 6th | Dec 7th | Dec 8th
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Tanisha Bhardwaj | Python modules and libraries | Done |  | Overview of Project | Presented the project statement | learnnt about creation of virtual Environment | Intro to tech tools to work with | Project presenting Session | Practised Python Concepts and overviw of project | Revision of previous concepts | learnt about the prompt engineering and its use cases | learnt about Ai,DS,Gen Ai ,fundamentals of llm | About llm and Groq API | hands on implementation | about package concepts using examples and workflow | Revised all the previous concepts done | revision and hands on practice
[9 empty] | 8th Dec | 9th Dec | 10th Dec | 11th Dec | 12th Dec | 13th Dec | 14th Dec | 15th Dec | 16th Dec | 17th Dec | 18th Dec | 19th Dec | 20th Dec | 21st Dec
3 |  | Clause Identifi cation and Risk Analysis Engine | Dec 8th | Dec 24th | Tanisha Bhardwaj | Understood about the LLM and hands on execution of the project | Done |  | Overview of the workflow and project structure | understanding of Workflow and extracting text to pdf | Extraction of text from pdf and Overlapping Concept | bried understanding about Cleaning the clauses and chunking | Understanding about clause identification and extraction | revision of previous topics and hands on implementation | brief revision about lama model and llm revision | delivery of assignment content and brief discussion about that | discussion on risk engine analysis and hands on implementation | discussion on run and pipeline Codes and brief Intro for Regulatory Update Tracking | Practise of both milestones 1 and 2 | Regulatory update Tracking | Practice and Assignment 1 (Task1-2) | worked on both tasks
[9 empty] | 2026-12-25 | Dec 27rth | Dec 28th | Dec 29th | 2026-12-30 | 2026-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2009-01-01 | 2010-01-01 | 2011-01-01 | 2012-01-01 | 2013-01-01
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Tanisha Bhardwaj | Update tracking and contract modification | Done |  | Practising over both tasks | Assignment presentation | Bried understanding about Regulatory update Tracking | Studied about regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | skimmed the concept of regulatory update tracking | practiced milestone-3 demo codes | Revision of previous modules | revised milestone 3 topics | Hands on with milestone 3 | Milestone 3 practicsed | FeedParser and executed milestone-3 codes | Hands on implementation of slack integration | Practise of Slack Integration | Google sheet Integration | Email Integration | Practised | Project Implemation | Mock Presentation
Note on D3: ====== ID#AAABv5noruQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E3: ====== ID#AAABv6zxceE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I4: ====== ID#AAABv6zxceM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J4: ====== ID#AAABv6zxceY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K4: ====== ID#AAABv6zxceU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L4: ====== ID#AAABv6zxceA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M4: ====== ID#AAABv5noruA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N4: ====== ID#AAABv5noruI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O4: ====== ID#AAABv6zxcec Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P4: ====== ID#AAABv6zxceI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q4: ====== ID#AAABv6zxcd4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R4: ====== ID#AAABv6zxcd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S4: ====== ID#AAABv5noruM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T4: ====== ID#AAABv5noruU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U4: ====== ID#AAABv6zxceQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V4: ====== ID#AAABv5noruE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W4: ====== ID#AAABv6zxcd0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7